## START HERE
🎉 EVENT PLANNING CHECKLIST & BUDGET
Complete Event Manager & Vendor Tracker Google Sheets
STEP 1 — Fill in “Tasks”
Complete event planning checklist with owner and deadline.
STEP 2 — Fill in “Budget”
Event budget by category with actual vs planned.
STEP 3 — Fill in “Guests”
Guest list with RSVP, dietary needs, and plus-ones.
STEP 4 — Fill in “Vendors”
Vendor contacts, contracts, and payment status.
Then open the Dashboard — everything calculates automatically.
TIP: Delete the sample rows once you've seen how it works.
TIP: On Google Sheets? File → Make a copy first, then edit your copy.
TIP: Columns with dropdowns keep your data clean — use them.
Need help? Message NasriTools on Etsy — I reply fast. 🧡

## Tasks
Task | Owner | Status | Due Date | Notes
Kickoff meeting | Sarah | Not Started | 2026-06-01
Send proposal | Sarah | In Progress | 2026-06-07 | Paid
Review feedback |  | Done | 2026-06-13 | Urgent
Update website copy | Sarah | Cancelled | 2026-06-16 | Follow up Friday
Prepare invoice | Sarah | Not Started | 2026-06-22
Client call |  | In Progress | 2026-06-28 | Monthly
Design first draft | Sarah | Done | 2026-06-03 | Confirmed
Fix reported bug | Sarah | Cancelled | 2026-06-09
Weekly report |  | Not Started | 2026-06-15 | Waiting reply
Plan next sprint | Sarah | In Progress | 2026-06-18 | Done early
Publish blog post | Sarah | Done | 2026-06-24
Team sync |  | Cancelled | 2026-06-02 | Recheck

## Dashboard
📊 EVENT PLANNING CHECKLIST & BUDGET — DASHBOARD
DAYS TO EVENT | TOTAL BUDGET $ | TOTAL SPENT $ | TASKS DONE
WHAT'S INSIDE
✅ Tasks — Complete event planning checklist with owner and deadline.
💰 Budget — Event budget by category with actual vs planned.
👥 Guests — Guest list with RSVP, dietary needs, and plus-ones.
📋 Vendors — Vendor contacts, contracts, and payment status.
Numbers update automatically as you fill the other tabs. Start with sample data deleted.

## Budget
Category | Description | Budget $ | Actual $ | Difference
Venue | Downtown event venue | 2000 | 1850
Catering | Downtown event venue | 1400 | 1295
Decorations |  | 2600 | 2405
Entertainment | Downtown event venue | 1700 | 1572
Photography | Downtown event venue | 2300 | 2128
Invitations |  | 1200 | 1110
Gifts | Downtown event venue | 2900 | 2682
AV Equipment | Downtown event venue | 1900 | 1758
Other |  | 2500 | 2312
Venue | Downtown event venue | 1600 | 1480
Catering | Downtown event venue | 2200 | 2035
Decorations |  | 1500 | 1388

## Guests
Name | Email | RSVP | Plus One | Dietary
Alex Martin | alex@mail.com | Yes | Yes | None
Sara Lopez | sara@mail.com | No | No | Vegetarian
Omar Haddad | omar@mail.com | Pending | Yes | Vegan
Emma Fischer | emma@mail.com | Yes | No | Halal
Liam Carter | liam@mail.com | No | Yes | Kosher
Nadia Rahali | nadia@mail.com | Pending | No | Gluten-Free
Tom Becker | tom@mail.com | Yes | Yes | Other
Julia Romero | julia@mail.com | No | No | None
Karim Ziani | karim@mail.com | Pending | Yes | Vegetarian
Anna Kowalska | anna@mail.com | Yes | No | Vegan
David Chen | david@mail.com | No | Yes | Halal
Lea Moreau | lea@mail.com | Pending | No | Kosher

## Vendors
Vendor | Service | Contact | Phone | Quoted $ | Status
BrightWave Studio | Catering | Alex Martin | +1 555 234 5678 | 3000 | Shortlisted
GreenLeaf Co. | Catering | Sara Lopez | +1 555 234 5679 | 2100 | Hired
Nova Digital |  | Omar Haddad | +1 555 234 5680 | 3900 | Contract Signed
Atlas Consulting | Catering | Emma Fischer | +1 555 234 5681 | 2550 | Deposit Paid
Pixel & Co | Catering | Liam Carter | +1 555 234 5682 | 3450 | Paid In Full
Blue Harbor Ltd |  | Nadia Rahali | +1 555 234 5683 | 1800 | Shortlisted
Sunrise Media | Catering | Tom Becker | +1 555 234 5684 | 4350 | Hired
UrbanCraft | Catering | Julia Romero | +1 555 234 5685 | 2850 | Contract Signed
PrimeWorks |  | Karim Ziani | +1 555 234 5686 | 3750 | Deposit Paid
EchoLab | Catering | Anna Kowalska | +1 555 234 5687 | 2400 | Paid In Full
Vertex Group | Catering | David Chen | +1 555 234 5688 | 3300 | Shortlisted
ClearPath Inc |  | Lea Moreau | +1 555 234 5689 | 2250 | Hired