## START HERE
📋 PROJECT MANAGEMENT DASHBOARD
Tasks, Milestones & Team Tracker Google Sheets
STEP 1 — Fill in “Tasks”
All project tasks with owner, deadline, priority, and status.
STEP 2 — Fill in “Milestones”
Key project milestones with target dates and completion status.
STEP 3 — Fill in “Team”
Team directory with roles, workload, and task count.
Then open the Dashboard — everything calculates automatically.
TIP: Delete the sample rows once you've seen how it works.
TIP: On Google Sheets? File → Make a copy first, then edit your copy.
TIP: Columns with dropdowns keep your data clean — use them.
Need help? Message NasriTools on Etsy — I reply fast. 🧡

## Tasks
Task | Assigned To | Due Date | Priority | Status | Phase | Notes
Kickoff meeting | Sarah | 2026-06-01 | 🔥 Critical | Not Started | Design
Send proposal | Sarah | 2026-06-07 | High | In Progress | Design | Paid
Review feedback |  | 2026-06-13 | Medium | Review |  | Urgent
Update website copy | Sarah | 2026-06-16 | Low | Done | Design | Follow up Friday
Prepare invoice | Sarah | 2026-06-22 | 🔥 Critical | Blocked | Design
Client call |  | 2026-06-28 | High | Overdue |  | Monthly
Design first draft | Sarah | 2026-06-03 | Medium | Not Started | Design | Confirmed
Fix reported bug | Sarah | 2026-06-09 | Low | In Progress | Design
Weekly report |  | 2026-06-15 | 🔥 Critical | Review |  | Waiting reply
Plan next sprint | Sarah | 2026-06-18 | High | Done | Design | Done early
Publish blog post | Sarah | 2026-06-24 | Medium | Blocked | Design
Team sync |  | 2026-06-02 | Low | Overdue |  | Recheck

## Dashboard
📊 PROJECT MANAGEMENT DASHBOARD — DASHBOARD
TOTAL TASKS | COMPLETED | IN PROGRESS | OVERDUE
WHAT'S INSIDE
✅ Tasks — All project tasks with owner, deadline, priority, and status.
🎯 Milestones — Key project milestones with target dates and completion status.
👥 Team — Team directory with roles, workload, and task count.
📊 Timeline — Project completion summary and phase-by-phase breakdown.
Numbers update automatically as you fill the other tabs. Start with sample data deleted.

## Milestones
Milestone | Target Date | Owner | Status | Notes
Kickoff meeting | 2026-06-01 | Project Lead | Upcoming
Send proposal | 2026-06-07 | Project Lead | In Progress | Paid
Review feedback | 2026-06-13 |  | Completed | Urgent
Update website copy | 2026-06-16 | Project Lead | At Risk | Follow up Friday
Prepare invoice | 2026-06-22 | Project Lead | Delayed
Client call | 2026-06-28 |  | Upcoming | Monthly
Design first draft | 2026-06-03 | Project Lead | In Progress | Confirmed
Fix reported bug | 2026-06-09 | Project Lead | Completed
Weekly report | 2026-06-15 |  | At Risk | Waiting reply
Plan next sprint | 2026-06-18 | Project Lead | Delayed | Done early
Publish blog post | 2026-06-24 | Project Lead | Upcoming
Team sync | 2026-06-02 |  | In Progress | Recheck

## Team
Name | Role | Tasks Assigned | Tasks Done | Status
Alex Martin | UI Designer | 8 | 5 | Available
Sara Lopez | UI Designer | 5.6 | 3.5 | Busy
Omar Haddad |  | 10.4 | 6.5 | On Leave
Emma Fischer | UI Designer | 6.8 | 4.25 | Overloaded
Liam Carter | UI Designer | 9.2 | 5.75 | Available
Nadia Rahali |  | 4.8 | 3 | Busy
Tom Becker | UI Designer | 11.6 | 7.25 | On Leave
Julia Romero | UI Designer | 7.6 | 4.75 | Overloaded
Karim Ziani |  | 10 | 6.25 | Available
Anna Kowalska | UI Designer | 6.4 | 4 | Busy
David Chen | UI Designer | 8.8 | 5.5 | On Leave
Lea Moreau |  | 6 | 3.75 | Overloaded

## Timeline
📈 TIMELINE
Project Summary
Total Tasks
Completed
Completion Rate